## Project progress
Project | 2025-08-01 |  |  |  | 2025-09-01 |  |  |  | 2025-10-01
| IPC: Filled-in all data to form and retrive record |  |  |  | IPC: Work flow approve process with attached document |  |  |  | IPC: Work flow approve process with alert notification mail or any other
| Car stagining: Recover code back 30 % |  |  |  | Car stagining: Recover code back 70 % |  |  |  | Car stagining: Can recover back all as previous
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
IPC | Car stagining: Recover code back 30 % W1: การบันทึกข้อมูลทั่วไป การทดสอบการสร้าง pdf ให้แสดงผลภาษาไทย
Car staging | Car stagining: Recover code back 30 % W1: แก้ไขหน้าจอการจองใหม่ และให้ตรงตามเงื่อนไขใหม่
PO Log | Car stagining: Recover code back 30 % W1: ทำหน้าจอเลือกข้อมูลและดึงข้อมูลจาก database กำลังแก้ไขเพิ่มเติมในส่วนของข้อมูลที่ทาง user ต้องการเพิ่ม

## AX Service
Project and Incident support | 2025-08-01 |  |  |  | 2025-09-01 |  |  |  | 2025-10-01
| Get handover as successor |  | Help to support once staff busy and cooperate in Critical or urgent case and continue remain project support as senior |  | Help to support once staff busy and cooperate in critical or urgent case and continue remain project support as senior |  |  |  | Help to support once staff busy and cooperate in critical or urgent case and continue remain project support as senior
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Hand over task

## E-Auction and other related
Project and Incident support | 2025-08-01 |  |  |  | 2025-09-01 |  |  |  | 2025-10-01
| Get handover as successor |  | Help to support once staff busy and cooperate in Critical or urgent case and continue remain project support as senior |  | Help to support once staff busy and cooperate in critical or urgent case and continue remain project support as senior |  |  |  | Help to support once staff busy and cooperate in critical or urgent case and continue remain project support as senior
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Hand over task

## Supervisor role
Action | 2025-08-01 |  |  |  | 2025-09-01 |  |  |  | 2025-10-01
| Get handover as successor |  | -Supervise staff -Cooperate with user or vendor if critical case. -Document contract verify and approve |  | -Supervise staff -Cooperate with user or vendor if critical or special case -Document contract verify and approve |  |  |  | -Supervise staff -Cooperate with user or vendor if critical or special case -Document contract verify and approve
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4